## Gap Analysis
Overview | Gap Analysis
Current State | Future State | Gap | Actions
Activity #1
What is the current state of your workgroup's activity #1? | What is the desired future state for actvity #1? | Define the gap between the current and future state. | What work must be done to close the gap?
Ex. Student Success Team action plan created. | Ex. Operational Student Success Team per Academic & Career Pathway | Ex. Personel, budget, training, and launch | Ex. Recruit/assign [describe in detail], provide training [describe], allocate budget [describe], and launch for fall 2022 implementation. Describe in detail in the action plan. (See the action plan template tab below and the action plan example).
Activity #2
What is the current state of your workgroup's activity #2? | What is the desired future state for activity #2? | Define the gap between the current and future state. | What project work must be done to close the gap?
Activity #3
What is the current state of your workgroup's activity #3? | What is the desired future state for actvity #3? | Define the gap between the current and future state. | What project work must be done to close the gap?
Add as many rows/activities as needed.
Dr. Al Solano, Continuous Learning Institute
Access more free resources at CLI.

## Action Plan Template
Purpose Statement:
Strategy: | Actions | Responsible Person(s) or Group(s)2 | Budget (if needed) | Timeline | Status Report | Challenges? | Support Needed?

## Action Plan Example
Strategy: | Actions: | Responsible Person(s) or Group(s) | Budget (if needed) | Timeline | Status Report | Challenges? (Use this column as you implement) | Support Needed? (Use this column as you implement)
Peer-to-Peer Mentoring | 1. Selection of Mentors: 20 mentors per semester will be students who are enrolled and currently have a 3.0+ cumulative grade point average, and are willing to commit 2 hours per week for meetings with their mentee(s) and 1 hour bi-monthly for meeting with other mentors and the Lead. Mentors will be mature, trustworthy and enthusiastic students who want to help others succeed. Incentives, besides altruistic, need to exist for mentor accountability and the success of the program. | John Hernandez & Ashanti Jones | 20 x 15/hr x 32 weeks per year = $9,600 | For spring implementation: By October 15th |  | We struggle to find students. | Faculty in the team spread their word in their sections and connected with student services to spread the word.
| 2. Mentor Training: An initial mentor training session will take place before the mentors meet their mentees. A Peer Mentoring Handbook will be developed by the program faculty lead. Mentors will be required to keep a journal where they will review and analyze their sessions. They will share their findings with the other mentors and the program lead at their monthly meeting. | John Hernandez & Ashanti Jones |  | For spring implementation: By November 15th
| 3. Mentee Orientation: The mentee orientations will give students details of the program and its benefits and convey mentee responsibilities, such as willingness to proactively address academic needs and challenges and take responsibility for fulfilling their commitments to the program. | John Hernandez & Ashanti Jones |  | By Feburary 1, beginning of spring semester
| 4. Mentor- Mentee Matching: A questionnaire will be used by the program faculty lead to make the best matches between mentors and mentored students. Questions related to their academic majors, hobbies, other interests, what they do for fun, and/or what kind of music they like will be used to help match the mentee to the mentor. It will be critical to mentor students in courses with low student success rates. | John Hernandez & Ashanti Jones |  | By Feburary 20, beginning of spring semester
| 5. Mentor- Mentee Meetings: Mentoring groups will meet twice every week for an hour. During these meetings, the mentors work with their mentees to improve their study habits, and teach them to work smarter and more efficiently. The mentors will act as role models for their mentees, share their particular expertise in different areas, and emphasize life-management skills, such as time management, dealing with conflict, and skills for coping with school-related stress. | John Hernandez & Ashanti Jones |  | Beings March 1st
Math & Bio Faculty Collaboration: Creating Contextualized Materials | Step 1: Faculty review topics for Biology I & II & College Algebra and Trigonometry as sequenced by course syllabus | Mark Cornell, Biology Faculty, Janet Bautista, Math Faculty | 4 faculty x $500 stipend = $2,000 | For fall 2022 implementation, by November 15, 2021 |  | We struggled to include more faculty. | The team found funding available to provide modest stipends.
| Step 2: Faculty collaborate to align biology course topics with relevant college algebra & trigonometry concepts | Mark Cornell, Biology Faculty, Janet Bautista, Math Faculty |  | By end of spring 2022
| Step 3: Supplemental materials prepared in time for workshop implementation. Two workshops (one for college algebra and one for trigonometry with calculation problems related to biology) will be held twice a week for at least two hours | Mark Cornell, Biology Faculty, Janet Bautista, Math Faculty |  | Implement beginning fall 2022
| Step 4: Supplemental materials delivered via tutoring workshops | Mark Cornell, Biology Faculty, Janet Bautista, Math Faculty |  | Implement beginning fall 2022
| Step 5: Monthly tudent evaluations inform student satisfaction with the workshop and overall helpfulness. | Mark Cornell, Biology Faculty, Janet Bautista, Math Faculty |  | Implement beginning fall 2022